## Slide 1: Poland O4 – Project ARES Kick-off meeting – 14 March 2007
Danielle Nowakowski
14 March 2007

## Slide 2: Agenda
Purpose of Kick-Off Meeting 5 mins
Introduction & Principles 5 mins
Merchandising Initiative Progress 5 mins
Review Progress 15 mins
  Objective
  Team Structure
  Scope
  Timing
Project Approach: 10 mins
  Risk Management
  Project Communication
  Quality Management
  Scope Change Management
Next Steps 5 mins
 Please feel free to ask questions during the presentation!

## Slide 3: Purpose of Kick-Off Meeting
Review Progress to Date
Review & Align to Project Approach
Officially move into the BUILD Phase!
Agree on Next Steps

## Slide 4: Introductions
<number>
Who’s in the call?

## Slide 5
Principles
2
Accountability
1
Alignment
3
Commitment
+
+
=
Successful Team!

## Slide 6: Merchandising Initiative Background
Portugal identified as first pilot market
  Capability; Action Notification & Audit
Poland and Canada identified as the next pilot markets: end of Q4 2007
USA Design is underway
Successful adoption in the Pilot markets will qualify the application to become the global solution.
Retail Excellence: Our pioneering solutions empower Retail Experts in all corners of the world to win at the First Moment Of Truth every time.

## Slide 7
Progress so far - Poland
Project Objective
Project Structure
Scope
Timing

## Slide 8: Poland Project Objective
Objective:
Poland wants a simple and effective tool to drive traditional Retail Excellence!
The delivery of a Store Connect solution will allow Poland to:
1. Meet Key Objectives of Retail Operations:
  Increase capacity
  Clearly set priorities
  Continuity of experiences for HQ & Operations
2. Meet Key Objectives of CBD:
  Win for P&G in store
  Build local business
  Fast, quality data to CBD

## Slide 9: Team Structure – Project ARES
Project Board
Cuneyt Yavuz, Richard Reed, Marcin Szlapski, Marcin Brzozowski
Thilo Press, Evgueni Iagniatinski , Martin Chladek
Karen Winney, Stephen Marosi
Jarek Gula (Local Project Manager- E2E)
Martin Chladek (CEEMEA Service Manager)
Dave Barker (Project Manager O4)
Kuba Kocinski (Store Connect Application Owner)
Jutta Dries (Poland SME)
Brian Beck (Store Connect Engineer)
Richard Lancaster (Store Connect Retail Analysis )
Danielle Nowakowski (Delivery Manager )
Adam Turczak (Key Stakeholder – Retail Ops)
Arek Korba (Key User – Unit Manager)
Inga Gniadek (Key User – Account Manager)
Stephan Leber (QA & Test)
Gate Review Team:
Adam Turczak, Martin Chladek,
Evgueni Iagniatinski, Jarek Gula,
Danielle Nowakowski
Karen Winney (Decision maker)

## Slide 10: Scope – Project ARES, Phase 1 Complete Go Live: July 07
On Handhelds:
~43 Account Managers
Head Office Management & Reporting
1 Operations Administrator
7 Unit Managers
1 Retail Operations Leader
15 Account Handlers
1-2 MS&P Managers
Connecting the field to the head office:
Hand Held & Synchronization via laptops

## Slide 11: Scope – Project ARES, Phase 1 cont’d Complete Go Live: July 07
Sectorization
Automated Weekly Call Scheduling
Promotions – OPTIMA & Local
Distribution Checks & Issue Management
Standard Territory & Employee Management
Surveys for Initiatives by Brand
Banner & Store Assortments
Operations Action Plan (OAP)
Local Interfaces
Standard O4 Reporting
Flexible work with In-Store Results.

## Slide 12: Out of Scope – Project ARES
<number>
Expanded functionality:
  Outsourced Sales Reps
  Scanning and Picture-taking
  Merchandiser Work Orders
  POSM stock-level calculation based on work orders
  Transfer orders for POSM
  Advanced reports
External applications POSM and Merchandising
Complete incorporation of global best practices and standards

## Slide 13: Project Plan – Key Milestones
Discover – Project Establishment
Analysis & Design
Design Sign Off
Infrastructure & Server Set Up
Build
Business App’n Development
Load O4 Application
System Integration Test (SIT)
User Acceptance Test (UAT)
Training (18-22 June 2007)
GO-LIVE (26 June 2007)
Post GO-LIVE
Dec.
Jan.
Feb.
Mar.
Apr.
Com-
pleted
Status
100 %
100 %
100%
PLAN
80 %
5 %
5 %
0 %
0 %
0 %
0 %
PLAN
PLAN
PLAN
0 %
PLAN
May
Jun.
Jul.
PLAN
PLAN
PLAN

## Slide 14
Project Approach:
Quality
Communication
Risk & Issues
Scope Changes

## Slide 15: Project Approach – the Phases
<number>
All O4 Projects are divided into phases:
  Phase 1 DISCOVER (Business Case, Scope, Plan)
  Phase 2 DESIGN (Analyze, Design)
  Phase 3 QUALIFY (Build, System Integration Test, Performance Test)
  Phase 4 READY (User Acceptance Test, Deploy)
  Phase 5 LAUNCH (Post Deployment)
We’ll check for quality at the end of each phase, looking for:
  Stage Gate Criteria - Passed
  Critical Path Schedule – Deliverables Met
Always looking out for risks & issues
  Look for Opportunities & Threats to the project
  Act to eliminate or reduce!

## Slide 16: Open Communication
Weekly Project Meetings
Board Reviews with MDO
Store major documents on the C&CS Plant website
Notes: Weekly status call with the Project Team on Monday, 2pm CET
  Weekly status report emailed
  One Tracker updated as required
  The weekly call may be extended to twice per week (Friday) if required.
  “Monthly” Project Board Meetings
Gate Review (Meetings) as defined in CPS
Escalation process established
  Includes Business Management (board)

## Slide 17: Managing Scope & Changes
<number>
The final Design Document has been signed off!
We will investigate all requests for changes, and assess with O4:
  Feasibility
  Complexity
  Effort & Cost
Finally, decide if we should implement the change:
  Business Justification (Value)
  Impact on quality, time, cost (including resources)

## Slide 18: Next Steps
Weekly Status Review – look for the updates!
Interface Design

## Slide 19
<number>
Q&A
?